## Instructions
IATI Implementation Schedule for: |  |  |  | Norwegian Refugee Council
IATI Organisation Identifier: |  |  |  | NO-BRC-977538319
(Click on hyperlink above for more information on IATI Organisation Identifiers)
Version: |  | 1.0 | Date: | 30 March 2012
This document provides a publication plan which covers:
1. When will data be published? Timetable and frequency of publication
2. Exclusions and constraints: Overview of exceptions, thresholds & constraints
3. How will data be published? How published data will be presented to users
4. What data will be published? Overview coverage. For each area of the standard:
a. Timetable for publication
b. Terminology used within the data provider's systems
c. Exceptions, thresholds & constraints
Instructions for completion:
The Implementation Schedule is divided into three tabs, with mirrored guidance tabs providing more help in completing the schedule (which should be deleted prior to submitting a completed Implementation Schedule):
1. Publishing Information
2. Organisation Data
3. Activity Data
Publishing Information
This provides space to provide more detailed information about what data will be published, whether there will be any exclusions, and how the data will be published.
This is made up of a mixture of boxes for extracting specific information and text boxes for providing more detailed information.
Many of the boxes for specific information consist of drop-down menus where you will need to select the most appropriate category that fits with the qualitative information you provide in the adjacent text box.
Some require a typed entry:
e.g. Numeric entry for % of total budget (/ODA) and date entries for publication timetable (this should appear in mmm-yy format - e.g. Jan-12).
The purpose of these boxes is to make it easier for users to extract the most pertinent information, whereas the text boxes expand on this to provide more detailed information.
Organisation Data and Activity Data
Although each of these has its own worksheet, the format for completing each is the same.
Each is made up of a table consisting of seven columns: 1) Information Area, 2) Status, 3) Publication date, 4) Exclusions & Thresholds, 5) Exclusion category 6) Data provider definition, and 7) Publication notes.
1) Information Area - this identifies the data item.
2) Status - this provides a traffic light rating on the readiness of data to be published and is based on the following key:
| Fully compliant | Publishing in full compliance with the IATI Standard
| Partially compliant | Publishing some data required by the IATI Standard
| Future publication | Data will be published at a future date
| Under consideration | No current plans to publish, but could be considered
| Unable to publish | Information not available or collected, or not relevant to organisation
(The colour coding is auto-generated through use of the drop-down menu.)
For anything less than full compliance, further information should be provided in the publication notes. This includes:
- dates for full compliance if partial compliance is expected initially
- information on future publication of data items - e.g. potential dates or what it is dependent upon (e.g. new management systems)
- under what conditions data items under consideration could be published (e.g. implementing geo-coding or collecting of results data)
- reasons for being unable to publish (e.g. not relevant to the organisation, not part of the organisation's business model, etc.)
3) Publication date - identifies when data can start being published (this will be based on the overall timetable for publication identified in the 'Publishing Information' tab, and should indicate when in the publication timetable this date item will be published).
The date should appear in mmm-yy format (e.g. Jan-12). If any additional information needs to be provided about the date, this should be added in the 'Publication notes'.
4) Exclusions & Thresholds - highlights any specific thresholds or exclusions for the data item.
5) Exclusion category - identifies the reason for the exclusion using the following drop-down menu:
| n/a | No exclusions
| a | Not applicable to organisation
| b | A non-disclosure policy
| c | Not currently captured and prohibitive cost
| d | Other (please specify within the 'Exclusions & Thresholds narrative)
6) Data provider definition - provides the terminology used within the organisation's internal systems (this demonstrates how internal terminology maps to IATI).
7) Publication notes - provides additional information, such as reasons for amber or red coding, or relevant information which is not covered in the preceding columns or requires further clarification.
Support available:
Knowledge Base
The Knowledge Base has a number of forums that provide additional information about getting started and implementing IATI, including discussions on tools, information for NGOs and some technical information.
Information on communication support can also be found here to help in promoting your IATI publication (including examples of existing news releases, templates and contacts).
The Knowledge Base can be found at:
http://support.iatistandard.org/forums
Further support
If you require any further support or there are any areas of information you would like to see added, please contact Joni Hillman at:
jhillman@bond.org.uk

## Publishing Information
1. When will data be published?
Timetable and frequency of publication
Which organisations/agencies/programmes will your IATI data cover? (What % of your total development flows does this cover? What is missing?)
| Percentage of total budget / ODA |  | Narrative
SCOPE | 6% |  | The Norwegian Refugee Council (NRC) currently publishes all minimum requirement IATI data items for all its DFID (Department for International Development) funded projects, both through its Programme Partnership Arrangement (PPA) and bilateral funding agreements. NRC is currently considering to expand the compliance to include projects funded by other donors.
Overall timetable for publication (Provide a date for when these organisations will publish (a) an initial (incomplete) set of IATI data and (b) full IATI implementation)
| Date of initial implementation | Date of full implementation | Narrative
TIMETABLE | 2012-12-31 | 2016-03-31 | a) An initial test period commenced in Q4 2012. Since March 2013 NRC has published (according to IATI minimum requirements) information on all its DFID funded projects. b)NRC has initiated a project to enhance its organisational transparency. This includes considering options to increase its compliance with IATI and other transparency initiatives. NRC has committed to develop an Information Disclosure policy by Q1 2015 as well as improving the quality and scope of its project data. NRC will also explore options to automate the process of converting data from our financial management system into xml format. These commitments have been agreed with DFID as a condition of its PPA funding for 2014 - 2016.
Timeliness and frequency of publication (How soon after data is captured and available internally will data be published? How frequently will data be published?)
| Frequency of publication | Timeliness of publication | Narrative
TIMEFREQ | Quarterly | 1 quarter in arrears | Most data will be updated quarterly, with approximately a quarter in arrears. New data will only be published once confirmation of funding is received from donors.
How early in lifecycle will activity details be published? (Will activity details be published during the pipeline/identification stage or not until they are approved and in the implementation stage)
| Lifecycle status at publication |  | Narrative
LIFECYCLE | Implementation |  | Data will only be published once an agreement has been formally signed and the project implementation has started.
Data quality status (Do you want to identify the status of the quality/audit/statistical verification of data that is published in registry? Please indicate whether you anticipate doing this, and the likely timing of moving from unverified data to verified data)
| Data quality |  | Narrative
DATAQUAL | Verified |  | The data will be verified by programme staff prior to publication. In some cases, donor approval will also be required prior to publication.
Approach to publication (Please outline what staff and system resources are being made available to implement IATI, any relevant organisational structures e.g. working groups, and who is leading on IATI implementation)
| System resource |  | Narrative
SYSRESOURCES | Excel spreadsheet conversion |  | Excel spreadsheet conversion will be used for initial publication. However, NRC aims to move towards automated publishing system by 2015.
Other notes
NOTES
2. What are the exclusions from publication?
Exceptions and constraints: general rules that exclude activities from being published. Any specific data item exclusions should be listed in the data tables (Organisation data tab and Activity data tab).
Thresholds (are there any thresholds on the value of activities or transactions to be published. Please specify what the general threshold limits are for publication)
THRESH | Annual project budgets will be published on a country level with the total annual value of each project (not per budget line).
Exclusions (Please identify any rules for excluding data or information that will either be applied automatically or used as a basis to manually exclude publication. Note that exceptions for publication should be kept to a minimum and based on existing national or other regulations)
EXCLUSIONS | Any exclusions will be made in line with the planned Information Disclosure Policy.
Any general issues or other constraints
OTHER
3. How will data be published?
Information for prospective users of information
Licensing (Under which license will data be published: public domain or attribution? If the license does not meet the IATI standard please specify why. Please state whether you intend to use the IATI authorised license or another)
| Licence type |  | Narrative
LICENCE | Public domain |  | Data will be published under a public-domain licence (using the Open Data Commons Public Domain Licence), according to the IATI standard.
Definition of an activity and multi-level activities (How is an activity defined e.g. projects and programmes, or some other structure? Do you have multi-tiered project structures e.g. projects and sub-projects or components? At which level do you intend to publish details (e.g. transactions)?)
| Multi-level activities reported? |  | Narrative
MULTILEVEL | No |  | NRC currently publishes information on a project level which specifies the geographical location and the type of programme core competency.
| Segmentation |  | Narrative
SEGMENT | Other |  | As the organisation's reported data is expanding, NRC will segment the data into project-based files in order to make the data easier to use. The three segmentations of data are as follows: one dataset for PPA projects 2011-2014, one dataset for PPA projects 2014-2016, and one dataset for stand-alone (bilateral) DFID funded projects.
Do you intend to provide a user interface in addition to raw (XML) IATI data? (Will IATI data be accessible for end users through an existing or a new user interface on your website? [Note: this is not an IATI requirement])
| User interface? |  | Narrative
USERINT | Under consideration

## Organisation Data
Organisation
| Note: definitions and code lists can be found at: |  |  | Note: For further information or support please go to the Knowledge Base:
| http://iatistandard.org/organisation-standard |  |  | http://support.iatistandard.org/forums
| Information Area | Status | Publication date | Exclusions & Thresholds | Exclusion category | Data provider definition | Publication notes
TOTALBUDGET | Annual forward planning budget data for agency | Under consideration | 2013-03-01 | As per planned Information Disclosure Policy/guidelines | c) Not currently captured and prohibitive cost | Overall annual budget for NRC by financial year. | NRC's overall annual budget (conservative estimate) is publishable (i.e. no detailed budget lines).
TOTALBUDGETORG | Annual forward planning budget for funded institutions | Unable to publish |  |  | a) Not applicable to organisation |  | NRC currently does not fund any institutions
TOTALBUDGETCOUNTRY | Annual forward planning budget data for countries | Under consideration | 2013-03-01 | As per planned Information Disclosure Policy/guidelines | c) Not currently captured and prohibitive cost | Overall annual budget for each NRC project by financial year. | Overall annual budget (conservative estimate) for each project is publishable (i.e. no detailed budget lines). Much of this is already published through donor and UN websites, e.g. http://fts.unocha.org/pageloader.aspx?page=search-reporting_display&CQ=cq141111141305mE8hjMkr1o&orderby=EmergencyYear&showDetails= and www.openaid.se
ORGDOCS | Organisation documents | Under consideration | 2013-03-01 | As per planned Information Disclosure Policy/guidelines | c) Not currently captured and prohibitive cost |  | Several organisation documents are currently publicly available, either on the internet (ww.nrc.no) or through hardcopy public documents.
Note on I11: Elizabeth Hendry: Do we know what type of organisation documents they are looking for?

## Activity Data
Activities
| Note: definitions and code lists can be found at: |  |  | Note: For further information or support please go to the Knowledge Base:
| http://iatistandard.org/activities-standard |  |  | http://support.iatistandard.org/forums
| Information Area | Status | Publication date | Exclusions & Thresholds | Exclusion category | Data provider definition | Publication notes
Identification
REPORTINGORG | Reporting Organisation | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Norwegian Refugee Council | Norwegian Refugee Council - IATI Organisation Identifier: NO-BRC-977538319
IATIID | IATI activity identifier | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | NRC project code
OTHERID | Other activity identifiers | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
Basic Activity Information
TITLEAGLANG | Activity Title (Agency language) | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | NRC Core Competences (Shelter, ICLA, Education, WASH, Food Security) and Advocacy
TITLERELANG | Activity Title (Recipient language) | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
DESCAGLANG | Activity Description (Agency language) | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Longer project description possibly including and sub components
DESCRELANG | Activity Description (Recipient language) | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
STATUS | Activity Status | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Whether the project is being implemented or has been closed.
STARTDATE | Activity Dates (Start Date) | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Start date of the project
ENDDATE | Activity Dates (End Date) | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Planned date for the project to finish or actual end date for closed projects.
CONTACTS | Activity Contacts | Partially compliant | 2013-03-01 | No individual staff names or contact details will be inlcuded a part from the Country Director. | b) A non-disclosure policy | NRC Country Office (Country Director) | Not a DFID minimum requirement
ORGFUNDING | Participating Organisation (Funding) | Partially compliant | 2013-03-01 | Exclusions may occur in some countries where information about donors may be percieved as particularly sensitive. This will be further developed in the planned Information Disclosure Policy/guidelines | c) Not currently captured and prohibitive cost | DFID | May be publishable in most cases.
ORGEXTENDING | Participating Organisation (Extending) | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
ORGIMPLEMENTING | Participating Organisation (Implementing) | Under consideration | 2013-03-01 |  | n/a (No exclusions) | NRC's implementing partners in country | Not a DFID minimum requirement
ORGACCOUNTABLE | Participating Organisation (Accountable) | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
Geopolitical Information
COUNTRY | Recipient Country | Fully compliant | 2013-03-01 | Project countries with no cross border activity to neighbouring countries | n/a (No exclusions) | Country where the project is being run
REGION | Recipient Region | Fully compliant | 2013-03-01 | Project countries with cross border activity to neighbouring countries | n/a (No exclusions) | Region where the project is being run, e.g. Colombia with neighbouring countries.
LOCATION | Sub-national Geographic Location | Under consideration |  |  | c) Not currently captured and prohibitive cost
Classifications
SECTORCRS | Sector (DAC CRS) | Under consideration |  |  | c) Not currently captured and prohibitive cost |  | Preferred DFID level of disclosure
SECTORAG | Sector (Agency specific) | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Clusters | Preferred DFID level of disclosure
POLICY | Policy Markers | Under consideration |  |  | c) Not currently captured and prohibitive cost |  | Not a DFID minimum requirement
COLLAB | Collaboration Type | Under consideration |  |  | c) Not currently captured and prohibitive cost |  | Not a DFID minimum requirement
FLOWTYPE | Default Flow Type | Under consideration |  |  | b) A non-disclosure policy | "Private grants" or "ODA" (Official Development Assistance). Initially only DFID funded projects will be reported. | Not a DFID minimum requirement
FINANCETYPE | Default Finance Type | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
AIDTYPE | Default Aid Type | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | CO1 | Not a DFID minimum requirement. CO1 (project type intervention),
TIEDAIDSTATUS | Default Tied Aid Status | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
Financial
BUDGET | Activity Budget | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Overall annual budget for each NRC project by financial year. | Overal annual budget (conservative estimate) for each project is publishable (i.e. no detailed budget lines).
PLANNEDDISBURSE | Planned Disbursements | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
RECCOUNBUDGETID | (UNDER DEVELOPMENT) Recipient Country Budget Identifier | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
Financial Transaction
COMMITMENT | Financial transaction (Commitment) | Fully compliant | 2013-03-01 |  | n/a (No exclusions) | Overall budget for NRC (PPA) | NRC's overall budget as per PPA (i.e. no detailed budget lines).
DISBURSEMENTEX | Financial transaction (Disbursement & Expenditure) | Partially compliant | 2013-03-01 |  | c) Not currently captured and prohibitive cost | Only Expenditure | NRC financial system does not distinguish between partners and contractors and it is thus currently impossible to separate these two dispursements. NRC will thus only report on Expenditure to start with, while consider whether Dispursements to partners can be included in the future.
REIMBURSEMENT | Financial transaction (Reimbursement) | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
INCOMINGFUNDS | Financial transaction (Incoming Funds) | Partially compliant | 2013-03-01 |  | c) Not currently captured and prohibitive cost | Overall annul transaction for NRC under the PPA | NRC's overall income from PPA
REPAYMENT | Financial transaction (Loan repayment / interest repayment) | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
Related Documents
ACTDOCS | Activity Documents | Partially compliant | 2013-03-01 | Depending on planned Information Disclosure Policy/guidelines | c) Not currently captured and prohibitive cost | Proposal, logframe, overall budget, reports, | NRC is considering to start publishing only executive summary of proposals and reports, but may later possibly consider to split the document in two (i.e. one public and one confidential part).
WEBSITE | Activity Website | Partially compliant | 2013-03-01 |  | c) Not currently captured and prohibitive cost | Overall programme activity in each country is currently available at www.nrc.no, but not on a detailed project level. | DFID Preferred Level of Disclosure. NRC is currently working at developing a Sharepoint platform for all projects, and will consider to what extent it will be possible in the future to publish information on project level.
RELACT | Related Activity | Under consideration |  |  |  |  | Not a DFID minimum requirement.
Performance
CONDITIONS | Conditions attached Y/N | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
TEXTCONDITIONS | Text of Conditions | Unable to publish |  |  | a) Not applicable to organisation |  | Not a DFID minimum requirement
RESULTS | Results data | Under consideration |  |  |  |  | Not a DFID minimum requirement. NRC has developed a Core Activity Database (CAD) in which Output and Outcome level results are captured. However, the user interface is not currently in place for publication and further development will be required.

## Drop-down menu (hidden)
Frequency | Timeliness | Lifecycle | Data quality | Staff resource | System resource
Real time | Real time | Pipeline/identification | Unverified | Dedicated resource | Manual capture through an online tool (web entry platform)
Weekly | 1 week in arrears | Implementation | Verified | Working group | Excel spreadsheet conversion
Fortnightly | 2 weeks in arrears | Other |  | Ad hoc | Direct feed from internal systems
Monthly | 1 month in arrears |  |  | Other | Other
Quarterly | 2 months in arrears
Bi-annually | 1 quarter in arrears
Annually | > 1 quarter in arrears
Other | Other |  |  |  | Exclusions
n/a (No exclusions)
|  | Multi-level type | Segmentation |  | a) Not applicable to organisation
License type |  |  |  | User interface | b) A non-disclosure policy
| Multi-level reporting | Related activities | Single file |  | c) Not currently captured and prohibitive cost
Public domain |  | Hierarchy | By country / region | Yes | d) Other
Attribution-only | Yes | Both | Other | In development
Other (non-compliant) | No |  |  | Under consideration
No
RAG
Fully compliant
Partially compliant
Future publication
Under consideration
Unable to publish