Terms of Reference

Global Mapping of National Data Systems on Internal Displacement

BACKGROUND

The Internal Displacement Monitoring Centre (IDMC) is the world's definitive source of data and analysis on internal displacement. Since our establishment in 1998 as part of the Norwegian Refugee Council (NRC), we have offered a rigorous, independent and trusted service to the international community. Our work informs policy and operational decisions that improve the lives of the millions of people living in internal displacement, or at risk of becoming displaced in the future.

IDMC has previously assessed national progress on displacement data through the Internal Displacement Index (IDI). The most recent IDI, published in 2023 as part of 25 years of progress on internal displacement 1998–2023, assessed progress across several dimensions of national responsibility, including a dedicated component on data on internal displacement.

The IDI provides an established foundation for assessing national progress on displacement data. IDMC now intends to revisit and update specifically the indicators relating to data on internal displacement, taking into account developments in national data practices and relevant statistical standards since the previous assessment.

The exercise will also expand the geographic coverage of the previous assessment. Rather than focusing on the countries covered by the previous IDI, the assessment will include a broader set of countries affected by disaster displacement, with the aim of establishing a more comprehensive global baseline of national displacement data systems.

The resulting assessment will form part of the planned enhancement of IDMC’s Global Repository of Good Practices on Internal Displacement (GRGP). In addition to documenting examples of good practice, the enhanced repository will provide structured country-level information showing where national displacement data systems exist, their key characteristics and where important gaps remain. The assessment will also provide an evidence base to inform IDMC’s data-related capacity-strengthening activities and identify opportunities for government-to-government peer learning on displacement data.

Within IDMC, the Global Insights Hub is responsible for all IDMC’s publications, including its flagship report, the Global Report on Internal Displacement, and for translating displacement data into accessible, policy-relevant insights. Under the supervision of the Global Insights Hub, the consultant will lead the assessment and produce the country-level evidence base, dataset and analysis required for integration into the enhanced GRGP.

CONSULTANCY OBJECTIVE

The objective of the consultancy is to update the data indicators developed through the IDI and apply them across an expanded set of countries to establish a global baseline of national systems for producing data on internal displacement.

Specifically, the consultancy will:

- review and update the existing IDI indicators relating to data on internal displacement, taking into account developments since the previous assessment;

- apply the updated indicators to an expanded set of countries affected by internal displacement, including broader coverage of countries affected by disaster displacement;

- assess the existence and key characteristics of nationally owned displacement data systems;

- identify progress and common gaps in national displacement data systems across countries and regions;

- identify relevant national practices and experiences that could inform capacity strengthening and government-to-government peer learning; and

- produce a structured country-level evidence base and analysis suitable for integration into the GRGP.

The assessment will focus specifically on national displacement data systems and their characteristics and gaps, rather than undertaking a broader assessment of countries’ institutional capacities to address internal displacement.

SCOPE OF WORK

Under the supervision of the Global Insights Manager, the consultant will undertake the following tasks.

- Inception note and updated data indicators

Following a review of the existing IDI data indicators and relevant developments since the previous assessment, the consultant will prepare a short inception note confirming the approach to the assignment.

In consultation with IDMC, the consultant will review the existing indicators and propose revisions or additions where needed to reflect developments in national displacement data systems and relevant statistical standards. The inception phase will also confirm the countries to be covered, assessment criteria, principal sources and approach to quality assurance.

- Country-level assessment and global dataset

Using the agreed indicators, the consultant will undertake a structured assessment of national displacement data systems across the countries included in the exercise.

The assessment will document the evidence supporting each country result and capture the key characteristics of the data systems identified, including relevant strengths and gaps. Particular attention will be given to national ownership of displacement data and, as appropriate to the agreed indicators, dimensions such as the types of displacement monitored, regularity of data production, geographic and demographic disaggregation, and accessibility of the resulting information.

The consultant will work with IDMC to ensure that the country-level information is structured in a format that supports integration into the enhanced GRGP and its interactive interface.

- Analytical report and final handover

Based on the country-level assessment, the consultant will prepare an analytical report presenting the principal findings of the exercise.

The report should:

- briefly describe the updated indicators and assessment approach;

- present the main global and regional findings;

- identify progress, patterns, strengths and common gaps in national displacement data systems;

- highlight relevant national practices and experiences;

- identify implications for IDMC’s data-related capacity-strengthening activities and opportunities for government-to-government peer learning; and

- provide recommendations for maintaining and periodically updating the baseline within the GRGP.

Following consolidated feedback from IDMC, the consultant will submit a final, publication-ready report and complete handover package.

KEY DELIVERABLES

- Updated IDI data indicators and assessment framework.

- Global country-level dataset on national displacement data systems.

- Country-level evidence for integration into the GRGP.

- Analytical report on national displacement data systems.

CONSULTANCY TIME and IMPLEMENTATION TIMEFRAME

This is a consultancy of up to 70 days over a period of 6 months, ideally starting in November. This is a home-based consultancy, with regular interactions via teleconferences.

The consultant will work in close coordination with IDMC’s Global Insights Hub throughout the assignment. The precise sequencing and deadlines for each deliverable will be agreed with the consultant at the start of the assignment and confirmed in the inception note.

PROFILE AND QUALIFICATIONS

Required:

- An advanced university degree in statistics, demography, economics, social sciences, development studies, humanitarian studies or another relevant discipline.

- At least seven years of relevant professional or research experience, including experience related to population, displacement, migration or official statistics.

- Demonstrated knowledge of internal displacement data and/or national statistical and administrative data systems, including how data are produced, managed and disseminated by government institutions.

- Demonstrated experience conducting multi-country research, comparative assessments or structured reviews using quantitative and qualitative indicators.

- Experience developing or applying assessment frameworks, indicators or classification systems, including the ability to apply criteria consistently across different country contexts.

- Strong quantitative and qualitative analytical skills, including experience compiling, managing and documenting country-level datasets from multiple sources.

- Demonstrated ability to critically assess the quality, coverage, ownership and limitations of data and data systems and to maintain a transparent evidence base for analytical findings.

- Strong research and writing skills, with demonstrated experience producing high-quality analytical reports for policy and/or technical audiences.

- Excellent written and spoken English.

Knowledge of international standards and recommendations relating to internal displacement statistics and official statistics, experience working with national statistical offices or other government institutions, and proficiency in French, Spanish, Arabic or other relevant languages would be considered strong assets.

Applicants must provide evidence of their legal registration, as applicable, and meet the relevant nationality and eligibility requirements; please refer to the How to apply section for full details.

MANAGEMENT and COORDINATION

The consultant will work under the supervision of IDMC’s Global Insights Hub and in close coordination with relevant colleagues across IDMC, particularly those working on data, monitoring, capacity strengthening and GRGP.

IDMC will provide the consultant with relevant background materials, including the previous IDI indicators and datasets, methodological documentation and other available information relevant to the assignment.

The consultant will be responsible for maintaining regular communication with IDMC throughout the consultancy, presenting progress at agreed milestones and incorporating consolidated feedback into the deliverables. Particular attention will be given to ensuring the consistent application of the assessment framework across countries and maintaining a clear record of the evidence and sources underpinning country-level assessments.

IDMC will review and validate the key deliverables. Where evidence is incomplete or requires further interpretation, the consultant will flag these cases for discussion with IDMC rather than making unsupported assumptions.

All datasets, methodological documentation, source records and other materials produced under the consultancy will be handed over to IDMC in editable and reusable formats at the conclusion of the assignment.

APPLICATION PROCESS

Qualified consultants are invited to submit a complete application on or before 23:59 (CET) Saturday 31 October 2026, through the email address ch.gvatenders@nrc.no. The bid application should be titled ‘IDMC Research Consultancy - Global Mapping of National Data Systems’ and include the following information:

- A CV highlighting relevant analytical, editorial and thematic experience.

- A short cover letter outlining their proposed approach and availability.

- A brief technical proposal of no more than two pages, demonstrating an understanding of the assignment and outlining the proposed approach to delivering the work.

- Two relevant writing samples such as analytical reports, multi-country assessments, research on displacement data or work relating to national statistical systems. Applicants should explain their role in producing each sample.

- A financial proposal indicating the proposed daily rate in CHF, inclusive of all costs and taxes.

- Contact details for two professional references.

- Certificate of incorporation (for legal entities) or proof of registration as a self-employed individual or independent consultant, in accordance with the legal requirements of the country of establishment or residence, as applicable. Kindly note that this assignment is partially implemented under an INTPA-funded contract. As such, the applicable nationality and eligibility rules for legal entities shall apply*. We regret that we will be unable to consider quotations from legal entities that do not comply with these nationality requirements.

* See ePRAG: PRAG 2021.1- Annex a2a1_ecprogrammes_eligibility2021_2027_en – NDICI-Global Europe - Global Challenges thematic programme.

Any request for clarification must be received by NRC in writing at least 5 working days before the deadline for submission of tenders. Questions regarding the assignment, can be addressed to Thannaletchimy Housset (thannaletchimy.housset@idmc.ch).

Please note: All service providers/consultants working with NRC should maintain high standards on ethical issues, respect and apply basic human and social rights, ensure non-exploitation of child labour, and give fair working conditions to their staff. NRC reserves the right to reject quotations provided by suppliers not meeting these standards. Consultants doing business with NRC will be screened on anti-corruption due diligence before NRC confirms a contract.

Anti-money laundering, anti-bribery, anti-corruption and anti-terrorism legislation and donor regulations require NRC to screen contractors against various international lists to ensure due diligence. Submission of the quotation constitutes acceptance of these screening practices.

NRC reserves the right to accept or reject the whole or part of your offer based on the information provided. Incomplete offers which do not comply with our conditions will not be considered.

We look forward to receiving your application!