REQUEST FOR PROPOSAL – NRC SUDAN – TERMS OF REFERENCE (TOR) FOR (END OF PROJECT EVALUATION) The Request for Proposal reference: RFP-SD-PZU-031 Evaluation Terms of Reference CASPIR (SIDA Development) End of Project Evaluation # Background information 1.1 Background on the context Sudan has been experiencing violent warfare and widespread civil unrest since April 2023, resulting in civilian casualties, large-scale displacement, and severe disruption of basic services. Against the backdrop of a protracted economic crisis and pre-existing conflicts across several regions, the escalation of hostilities has significantly increased humanitarian needs nationwide. Sudan remains one of the world’s most severe and neglected humanitarian crises. The number of people in need of humanitarian assistance has risen from 24.7 million in 2024 to 31.4 million in 2025, meaning that more than half of the country’s population now requires humanitarian support. The country is currently facing the largest displacement crisis in Africa, with over 13 million people displaced, including 9.1 million internally displaced persons (IDPs). Most displaced people are living in urban areas and within host communities where resources are increasingly strained, while others remain in overcrowded camps with limited services. Despite the scale of urban displacement, coordinated responses remain limited, with significant gaps in coverage and service delivery. Sudan is also experiencing the largest hunger crisis globally, with more than 21 million people (roughly half of the population) food insecure. The 2026 HNRP projects 28.9 million people in need of food security and livelihoods assistance. At the same time, conflict, inflation, and the destruction of infrastructure have severely disrupted livelihoods, markets, and basic services. Violence in areas such as Darfur and Kordofan continues to expose civilians to grave protection risks, including displacement, looting, and other forms of abuse. Humanitarian access remains constrained due to insecurity and restrictions by parties to the conflict, while funding shortages continue to limit the scale of the response. Suda n currently has a population of 51 million people, out of which 33.7m are in need and 20.4m are targeted for assistance. Of the $2.8 billion required for the humanitarian response in 2026, only 15.2 percent has so far been funded, forcing many organizations to scale back life-saving programmes. 1.2 NRC’s activities and presence NRC operates in Gedaref, White Nile, West and Central Darfur, South Darfur, North Darfur, and South and North Kordofan, with its country office in Port Sudan. NRC’s response in Sudan draws on its core areas of expertise: education, shelter, WASH, legal assistance, protection, camp management and livelihoods support delivered through cash and market-based approaches, to provide lifesaving assistance, dignified living conditions, and pathways for people displaced by conflict and disaster to rebuild their lives. NRC Sudan actively engages in all key national and subnational coordination forums. Through the cluster system, the Refugee Consultation Forum, and the INGO Forum, NRC plays a leading role in collaborative humanitarian efforts. The organization’s commitment to coordination extends beyond participation, as NRC consistently shares its technical knowledge and field expertise to strengthen collective responses. NRC Sudan serves as an active member of Strategic Advisory Groups, the Protection of Civilians Advisory Group to the Humanitarian Country Team, and the Cash Working Group. It co-chairs the Housing, Land and Property (HLP) Rights Area of Responsibility and the Technical Working Group for Group Cash Transfers (GCT) and remains a core member of the Operational Humanitarian Country Team and the INGO Forum Access Working Group. NRC Sudan also prioritizes state-level coordination within each operational area. In addition, NRC is involved in four consortia with INGOs—including the Rapid Response Mechanism and the Cash Consortium of Sudan—and acts as an observer on the Localization Coordination Council of Sudan’s Emergency Response Room. Through these diverse coordination mechanisms, NRC Sudan makes significant contributions to the Sudan Humanitarian Response Plan, ensuring all programs are fully aligned with HRP priorities. 1.3 NRC’s intervention specific to the evaluation Under the CASPIR project, NRC aimed to improve the living conditions of communities in South Kordofan and White Nile by strengthening climate resilience, promoting diversified and adaptable livelihood systems, and supporting more efficient, sustainable, and inclusive governance of natural resources, with particular focus on land and resource management. The project was designed to contribute to two long-term outcomes: Increased peaceful coexistence among targeted communities through the reduction of conflicts related to natural resources. Improved sustainability, diversification, and adaptability of livelihood options among targeted communities. To support the first outcome, NRC focused on strengthening community capacities to prevent and address land and natural resource disputes while promoting environmentally sustainable practices. Activities included training on Collaborative Dispute Resolution (CDR), awareness-raising sessions, and community participatory planning processes. The project also facilitated conflict-sensitive community assessments to identify key sources of tension and map stakeholders involved in natural resource governance. In addition, technical assistance was provided through legal support for community-based dispute resolution processes and demonstrations of improved agro-pastoral practices supported by extension services. The intervention also sought to strengthen the role and effectiveness of community structures and natural resource management committees, supporting communities to develop participatory action plans for more equitable and sustainable access to land and other resources. To achieve the second outcome, the project aimed to strengthen livelihoods and economic resilience by improving access to land, productive inputs, credit, and markets. Activities targeted different groups, including agro-pastoralists (farmers and pastoralists), community-based livelihood groups such as savings and seed groups, and market actors. The project supported capacity building, technical assistance, and linkages with market systems to improve production and income opportunities. In addition, NRC integrated Housing, Land and Property (HLP) support and access to legal and civil documentation (LCD) to strengthen tenure security and facilitate access to services and economic opportunities. These interventions aimed to enhance communities’ ability to manage land-related issues, improve access to legal identity, and support more sustainable and inclusive livelihood outcomes. Deadline for application is 9th of April2026 @ 16:00 (GMT +2) PROCESS FOR APPLICATION We are opened to provide further information (background of this assignment/consultancy, generic terms & conditions, information on award process) upon request. - Deadline for submission: 9th of April 2026 @ 16:00 (GMT +2) Complete Proposal documents must be submitted by EMAILS Email for submission: sd.procurement@nrc.no CONTENT OF REQUEST FOR PROPOSAL - Terms of reference - How to Apply Annex 1: Applicant checklist

- TERMS OF REFERENCE

# Purpose of the evaluation and intended use

## Overarching purpose

The purpose of this end-line evaluation is to assess the extent to which the Collaboration Across Societies for Peace, Inclusion and Resilience (CASPIR) project contributed to: - Strengthening climate resilience among target communities - Improving and diversifying livelihoods - Reducing tensions and promoting peaceful coexistence among agro-pastoralist communities - Enhancing access to basic services and rights, particularly through legal and civil documentation The evaluation will assess the project’s contribution to sustainable peace and resilience through inclusive, community-centred approaches, with a particular focus on women’s participation and empowerment. It will generate evidence on changes in: - Natural resource management practices - Economic stability and livelihood outcomes - Social cohesion and conflict dynamics - Women’s inclusion and participation - Access to services and legal identity Findings will inform learning, accountability, and future programming.

## How will the evaluation be used?

The evaluation will generate evidence on the effectiveness of the project’s interventions, including support to climate-resilient agriculture, livelihood diversification, financial inclusion, community-based natural resource management, and efforts to strengthen access to legal identity documentation and community dispute resolution (CDR) mechanisms. The findings will be used to inform learning, accountability, and adaptive management. Specifically, the results will support improvements to ongoing programming, inform the design of future initiatives in similar contexts, and contribute to organizational learning. The evaluation will also strengthen accountability to the donor, project stakeholders, and participating communities by providing evidence on the outcomes and impact of the project’s interventions, including progress in improving access to legal identity and strengthening community-based mechanisms for managing disputes and promoting social cohesion.

## Who will it be used by?

The findings of the evaluation will be used by NRC programme and management teams to assess the effectiveness of the project’s interventions and inform adaptive management and future programming in similar contexts. The results will also be shared with the donor and project partners to demonstrate accountability and provide evidence of outcomes achieved. Findings will strengthen future interventions aimed at promoting peaceful coexistence, sustainable livelihoods, improved natural resource governance and increased exercise of rights and access to basic services

# Scope and lines of inquiry

## Scope:

Dates of the evaluation: 19 April – 31 May 2026 Geographical coverage: White Nile (Rabak, Kosti and Gulli localities) and South Kordofan (Kadugli and Reif Al Shargi localities) States Projects: SDFM2212 Donors: SIDA DEVELOPMENT

## Lines of inquiry

The evaluation should answer: Did our program make a meaningful difference? The question drives us to ask what changed, and why and how the change happened.

# Methodology

Mixed methods approach, combining qualitative and quantitative data. The consultant will collect information that not only measures indicators but also helps triangulate and explain the findings, providing deeper insights beyond simple calculation. The methodology should include: Key Informant Interviews with community leaders, committees' members. Households' surveys Focus Group Discussions with members of groups and committees that were established and/or targeted through the project's activities. Field visits to project sites. Prior to filing data collection, enumerator will be trained on the basics of data collection, including the objective of the study, the structure of the questionnaires, and the use of tools The data collection will target all project beneficiaries and locations. The activities, number of beneficiaries and locations: Activity; Number of groups; Location; Methodology. VSLA; 58; White Nile; FGD and KII. Natural Resources Management; 8; White Nile; FGD and KII. Farmer Field Schools; 12; White Nile; FGD and KII. Livelihoods Groups; 57 36; White Nile South Kordofan; FGD and KII FGD and KII. Access to Agricultural Inputs (cash and vouchers); 3,672 3,772; White Nile South Kordofan; HH Survey. Financial Support to key market actors and early adopters; 434 33; White Nile South Kordofan; HH Survey. Training individuals in food production skills related to food and agriculture systems; 1,864 3,772; White Nile South Kordofan; HH Survey.

# Evaluation follow up and learning

The findings will be used to inform adaptive management and future programming in similar contexts. The results will also be used to demonstrate accountability and provide evidence of outcomes achieved. Findings will strengthen future interventions aimed at promoting peaceful coexistence, sustainable livelihoods, improved natural resource governance and increased exercise of rights and access to basic services. A management response will be developed within one month of the evaluation report being finalised. This will be followed up and tracked by MEAL Unit. A dissemination plan will be developed to ensure that important learning is shared with internal and external stakeholders.

# Management of the evaluation

An evaluation Steering Committee (SC) will be established by NRC, with the following members: Steering Committee chair: Head of Programme Support Manager Evaluation manager: MEAL Manager Steering committee members: LFS Coordinator, Durable Solutions Specialist, Partnership Manager, Head of Programmes The Steering Committee will oversee administration and overall coordination, including monitoring progress. The main functions of the Steering committee will be: - Establish the Terms of Reference of the evaluation. - Select evaluator. - Review and comment on the inception report and approve the proposed evaluation strategy. - Review and comment on the draft evaluation report. - Establish a dissemination and utilization strategy.

# Deliverables and reporting deadlines

- Week 1 (12 April to 16 April) - Inception Report - Week 2 to week 6 (19 April to 14 May) - Cleaned dataset - Week 7 (17 May to 21 May) Draft Report - Week 8 (21 to 26 May) Review Report and Validation Meeting - Week 9 (29 May to 31 May) Final Report

# Timeframe

Evaluation Start Date: April 2026 Key Dates: 19 April – 31 May 2026 (7 weeks) Dates for presentations/ participatory meetings: 17 – 21 May 2026 Final report deadline: 31 May

# Evaluation consultant team

NRC seeks expressions of interest from people with the following skills/qualifications - Senior humanitarian or development professional with a minimum of 10 years of relevant experience. - Proven experience in conducting organisational reviews, evaluations, or assessments. - Technical expertise in humanitarian programming, natural resource management, livelihoods, protection, and/or ICLA interventions. - Experience managing strategic projects, pilots, or multi-sector programs in complex humanitarian contexts. - Familiarity with the country context (Sudan) and the specific challenges of displacement, livelihoods, and community-based interventions. - Proficiency in evaluation and research methods, including both qualitative and quantitative approaches, data collection, and analysis. - Excellent English language skills (written and spoken). - Ability to provide technical guidance and support adaptive management based on evaluation findings. - Experience in triangulating data from multiple sources to inform evidence-based recommendations.

# -Application process and requirements

Application Deadline: Interview dates: Bids must include the following: - Proposal including, outline of evaluation framework and methods, including comments on the TOR, proposed time frame and work plan (bids over 3 pages will be automatically excluded). - Proposed evaluation budget - CVs Submit completed bids to (insert name)

- HOW TO APPLY: PROPOSAL (EMAIL)

The applicant(s) is/are expected to comply with the below requirements and submit the following:

- Submission of proposal via email - (attach two files for each technical and financial proposal) - sd.procurement@nrc.no

.

In both cases, please make sure to write on the subject of the email the reference of this Request for Proposal as follows:

FINANICAL PROPOSAL SUBMISSION (MANADATORY)

BID PRICE FOR SERVICE CONTRACT

- The contract will be awarded to a single bidder, unless otherwise specified in the Bid Data Sheet, all duties, taxes and other levies payable by the supplier/NRC under the contract, shall be included in the total bid price submitted by the bidder..

- The priced offer submitted by Bidders shall be checked for arithmetical errors and for what might be considered unreasonable rates during the evaluation. Where errors are identified one or more of the following steps may be taken

  - By default, the financial evaluation of the bid will be based on the unit rate of the line item,

  - If any rates are considered to be unrealistic or unreasonable, they may be altered by mutual agreement, provided that no alteration shall be made in the amount of the Bid.

  - If any arithmetical errors are detected in an otherwise acceptable bid, then the Bidder will be disqualified, the onus is on the Bidder to provide accurate information.

- The Bidder is reminded that it is entirely his responsibility to ensure the accuracy of their bid. No alteration will be made to the bid after its submission on the grounds of any arithmetical errors subsequently discovered except as provided above.

- The consultant will take on any international and local tax obligations within the contract value, including a 10% Tax payable by the consultant as per Sudanese government regulations, paid by NRC.

CURRENCIES OF BID AND PAYMENT

- All prices shall be quoted by the Bidder in EURO /USD unless otherwise stated. Similarly, all payments will be made in the same currency.

- By default, payment will be made within 30 days of completion of delivery and submission of all necessary documentation (Final Report). Failure to provide all necessary documents will result in delays

BID VALIDITY

- Bids shall remain valid for a period of 90 calendar days after the date of the bid submission deadline as prescribed by Norwegian Refugee Council.

- In exceptional circumstances, prior to the expiration of the bid validity period, the Norwegian Refugee Council may request Bidders in writing to extend the period of validity of their bids. A Bidder must confirm in writing his acceptance of the extension.

- Any corrections/ amendments must be initialled and stamped by the bid

Proposed Evaluation Criteria

- Technical Evaluation

| # | Criteria | Description | Score |
| --- | --- | --- | --- |
| 1 | Technical Expertise and Thematic Experience | Proven experience in conducting project evaluations or organisational reviews in humanitarian/development contexts. Strong expertise in Natural Resource Management (NRM), Livelihoods, Protection, and ICLA. Demonstrated ability to assess outcomes related to climate resilience, conflict sensitivity, Collaborative Dispute Resolution (CDR), and legal identity documentation. | 30 |
| 2 | Understanding of Sudan and Conflict Settings | Strong knowledge of the Sudan context, particularly displacement, conflict dynamics, and community-based interventions in White Nile and South Kordofan. Understanding of agro-pastoral systems, local governance structures, and humanitarian access constraints. | 20 |
| 3 | Proposed Methodology and Approach | Quality and feasibility of the proposed mixed-methods approach. Clear sampling strategy, data collection plan (HH surveys, FGDs, KIIs), and robust triangulation. Integration of gender, conflict sensitivity, and ethical considerations. Alignment with evaluation criteria (relevance, effectiveness, impact, sustainability). | 25 |
| 4 | Learning, Analysis, and Reporting Capacity. | Demonstrated ability to produce high-quality analytical reports, generate evidence-based findings, and provide practical, context-sensitive recommendations that support adaptive programming and learning. | 10 |
| 5 | Financial Offer (Cost-Effectiveness) | Realism, transparency, and value for money of the financial proposal. Assessment based on quality-cost balance, not lowest price.. | 15 |
| TOTAL |  |  | 100 |

ANNEX I - APPLICATION CHECKLIST (FOR THE APPLICANT TO FILL AND SIGN/ STAMP)

TO BE INCLUDED IN THEIR PROPOSAL

| Description – ANNEX I | To be filled by bidder Included? (yes/no) | To be filled by NRC |  |  |
| --- | --- | --- | --- | --- |
|  |  | Present & complete? |  | Comments |
| ENVELOP – TECHNICAL |  |  |  |  |
| CV of the applicants |  |  |  |  |
| Cover letter detailing the consultant’s qualifications and experience in undertaking similar assignments; |  |  |  |  |
| Copies of Consultant ID and address for screening purposes |  |  |  |  |
| Proof of consultancy registration/ Company profile |  |  |  |  |
| Tax Identification Number (TIN) registration certificate (Tax registration)- If any |  |  |  |  |
| Value Added Tax (VAT) registration certificate (if VAT is to be charged in the country of origin of the consultant) – if any |  |  |  |  |
| All necessary license certificates in line with government regulations |  |  |  |  |
| Envelop 2 – Financial |  |  |  |  |
| Section 6 – Pricing proposal - signed/ stamped |  |  |  |  |

To: Norwegian Refugee Council

Sir / Madam,

We offer to deliver the service in accordance with all requirements of the current Request for Proposal, Conditions of Contract and any other Binding requirements accompanying this Bid. We, the undersigned, verify that we are in compliance with all applicable laws and regulations, and meet the ethical standards as listed above or positively agree to these ethical standards and are willing to implement necessary changes in the organization.

This Bid signed by our authentic representative and your written award of it shall constitute the formation of a binding contract between us.

| Registered company name: |  |
| --- | --- |
| Any other trading names: |  |
| Any associated companies (cross holding/ joint ownership/ shareholding/ etc.) |  |
| Name of Signatory: | Date of Signing: |
| Title of Signatory: | Name of Bidder: |
| Signature & stamp: | Tel N°: |
|  | Email: |
|  | Address: |

| Bank name (to be used for this contract) |  |
| --- | --- |
| Account number |  |

Ethical Standards Declaration for all Supply, Service and Works Contractors

We, the undersigned, (‘we’, ‘our’ or ‘us’) CONSIDERING THAT:

FIRST, we are bidding for, or entering into, a contract with the Norwegian Refugee Council (NRC) to supply goods, services or works to NRC (‘the Contract’).

SECOND, we understand that as a humanitarian organisation, NRC expects its suppliers and contractors to have high ethical standards.

THIRD, we understand that NRC therefore needs us to confirm that we adhere to the required ethical standards (‘the ethical standards’) by signing this declaration (‘the Declaration’).

THEREFORE, we DO HEREBY DECLARE as follows:

- Declaration concerning compliance with applicable laws and these ethical standards

We declare that we shall:

- Meet the ethical standards in this declaration (‘ethical standards’)

- Ensure that any party representing us, including but not limited to:

•	board members

•	directors

•	employees

•	contractors or sub-contractors, and their employees

•	consultants and sub-consultants, and their employees;

•	other legal representatives

(‘our Representatives’) are aware of and comply with these ethical standards.

In the event that we, or our Representatives, do not meet the ethical standards at present, we shall:

- Explain to NRC in what way we do not currently meet the ethical standards

- Agree a plan and timeline with NRC to implement changes that allow us to meet the ethical standards

- Provide regular updates to NRC on the implementation plan.

- Declaration concerning status

We hereby declare that neither we, nor to the best if our knowledge our Representatives, are in any of the following situations:

  - Have made an offer, payment, consideration or benefit of any kind, which constitutes illegal or corrupt practice, directly or indirectly, as an inducement or reward in relation to the tendering, awarding or execution of the Contract.

  - Are involved in any form of fraud, corruption, collusion, coercive practice, bribery, involvement in a criminal organisation or other illegal activity

  - Are insolvent, in receivership, bankrupt, or being wound up

  - Have suspended activities

  - Are subject to legal proceedings related to 2.1

  - Have at any time been found guilty and sentenced by a court, whether in the country of employment or abroad, for a criminal offence in respect of children or vulnerable adults

  - Are engaged in:

•	terrorism or the material support of terrorism

•	the sale or manufacture, either directly or indirectly, of anti-personnel mines or any components produced primarily for the operation thereof

•	the sale or manufacture, either directly or indirectly, of weapons

•	the production of alcohol, tobacco, or pornography.

- Declaration concerning Conflicts of Interest

We declare that neither we nor, to the best of our knowledge, our Representatives have an undisclosed conflict of interest with NRC, in accordance with NRC’s Conflict of Interest Policy (the Policy).

Where any potential conflict of interest exists between our Representatives and NRC or any NRC staff member, we shall notify NRC in writing of the potential conflict using Form F in the Policy. We understand that the Policy and the Form is available on NRC’s website or that we can contact the NRC Procurement focal point, as mentioned in the tender documentation. NRC shall then determine whether action is required.

A conflict of interest can be due to a relationship with an NRC staff member such as family or friends.

We understand that if we fail to report a potential conflict of interest and are later found to have a conflict of interest, we may be removed from the NRC vendor database.

- Declaration concerning compliance with national law

We declare that we and, to the best of our knowledge, our Representatives:

  - comply with all applicable laws and regulations in effect in the country or countries where the Contract will be carried out.

  - comply with all applicable export laws concerning the country or countries where the Contract will be carried out.

  - are registered with the relevant government authority with regard to taxation for the duration of the Contract.

  - pay taxes according to all applicable national laws and regulations for the duration of the Contract.

- Declaration concerning compliance with labour standards

We declare that we and, to the best of our knowledge, our Representatives:

We declare that we and, to the best of our knowledge, our Representatives comply with applicable national labour law standards and the International Labour Organisation Declaration on Fundamental Principles and Rights at Work.

Specifically, we declare that we and, to the best of our knowledge, our Representatives comply with the following minimum labour standards:

  - Working Conditions

- All workers receive a contract of employment that is written in a language they understand.

- All workers are free to leave after giving reasonable notice.

- All workers have the right to join or form trade unions of their own choosing and to bargain collectively.

- No worker is required to lodge ‘deposits’ or identity papers or immigration documents in order to obtain employment.

  - Wages and benefits

  - Wages and benefits paid for a standard working week meet, at a minimum, national legal standards or industry benchmark standards, whichever is higher. Wages are always sufficient to meet basic needs.

  - No deductions from wages are made as a disciplinary measure.

  - Working time

  - Working hours comply with national laws and benchmark industry standards, whichever affords greater protection. Whenever possible working hours do not exceed 48 hours per week (8 hours per day).

  - Workers are provided with at least one day off for every 7-day period.

  - Health and safety

  - Steps are taken to prevent accidents and injury to health arising out of, associated with, or occurring in, the course of work, by minimizing, so far as is reasonably practicable, the causes of hazards inherent in the working environment.

  - Workers receive regular and documented health and safety training, and such training is repeated for new workers.

  - Workers have access to clean toilet facilities and to potable water, and, if appropriate, sanitary facilities for food storage is provided.

  - Accommodation, where provided, is clean, safe and adequately ventilated.

  - Discrimination and abuse

  - No worker is forced, bonded or an involuntary prison worker.

  - There is no discrimination at the workplace based on ethnic background, religion, age, disability, gender, marital status, sexual orientation, union membership or political affiliation.

  - Measures are in place to protect workers from sexually intrusive, threatening, insulting or exploitative behaviour, and from discrimination or termination of employment on unjustifiable grounds, e.g. marriage, pregnancy, parenthood or HIV status.

  - Physical abuse or punishment, or threats of physical abuse, sexual or other harassment and verbal abuse, as well as other forms of intimidation, are prohibited.

  - Persons under 18

- No persons under the age of 18 shall be engaged in work which is hazardous to their health or safety, including night work.

- The working hours and nature of work of any worker who is under the age of 18 shall not interfere with their opportunity to complete his or her education.

- Declaration concerning the environmental standards

We declare that we and, to the best of our knowledge, our Representatives comply with applicable national environmental law standards and with international environmental standards, to the greatest extent possible.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We respect national and international environmental legislation and regulation.

  - We ensure that production and extraction of raw materials for production does not contribute to the destruction of the resources and income base for marginalised populations, such as in claiming large land areas or other natural resources on which these populations are dependent.

  - We take environmental measures into consideration throughout the production and distribution chain ranging from the production of raw material to the consumer sale. This includes reasonable steps to minimise negative environmental impacts (e.g. emissions, water usage, waste) and to use - where possible - sustainable resources. Local, regional and global environmental aspects shall be considered. The local environment at the production site will not be exploited or degraded by pollution and waste.

  - We carefully manage hazardous chemicals and other substances in accordance with documented safety procedures.

- Declaration concerning protection from sexual exploitation and abuse

We and, to the best of our knowledge, our Representatives comply with international standards related to protection from sexual exploitation and abuse (PSEA) and sexual harassment.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We take sexual misconduct seriously and ensure that any employee found to have carried out sexual misconduct will be subject to disciplinary action.

  - We will ensure, that none of our employees engage in any sexual activity with persons (adult or child) in relation with this contract regardless of the age of majority or consent locally.

  - We will ensure that none of our employees produce, procure, distribute or use sexually explicit material in any activities under the Contract or on any sites used under the Contract.

  - We will ensure that none of our employees will exchange money, employment, goods or services for sex, including sexual favours or other forms of humiliating, degrading, or exploitative behaviour.  This prohibition extends to any use of sex trade workers.  If  any sexual misconduct is found to have taken place, such employees face disciplinary action.

  - We shall report any incident or complaint of sexual misconduct or child abuse related to the activities carried out under the Contract through NRC’s PSEA and Safeguarding Unit at psea@nrc.no.

  - We shall report any known or reported sexual relationship between our employees and NRC staff to NRC.

- Declaration concerning protection of children

We declare that neither we nor, to the best of our knowledge, our Representatives are engaged in any practice inconsistent with the rights set forth in the Convention on the Rights of the Child.  We commit to upholding international and national laws and policies regarding child safeguarding.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We support and protect the complainant, survivors and witnesses of any raised incidents or complaints of sexual misconduct or child abuse.

  - We will ensure, that our employees will not abuse or exploit children or act in a manner that may place a child at risk of harm.

  - We will ensure that our employees are not left alone with children.

  - We will ensure our employees will not ask children for personal contact details without a valid reason to do so.

  - We listen, to the best of our ability, to children’s views and opinions and treat boys and girls in a manner that is respectful of their rights and dignity during the performance of the Contract.

  - We shall report any suspicion of child safeguarding concerns through the Complaints and Feedback Mechanism, provided by the NRC contract focal point and at psea@nrc.no.

- Declaration concerning anti-human trafficking

We declare that neither we nor, to the best of our knowledge, our Representatives are engaged in trafficking in persons as defined in the protocol to Prevent, Suppress and Punish Trafficking in Persons or the UN Convention against Transnational Organized Crime.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We do not solicit persons for the purpose of employment, or offer employment by means of materially false or fraudulent pretences, representations, or promises.

  - We do not charge employees recruitment fees.

  - We do not provide or arrange housing for employees that does not meet host country housing and safety standards.

  - We commit to report any suspected violations of this clause to NRC immediately.

  - We commit to make our Representatives aware of the trafficking related prohibitions outlined above and share the Global Human Trafficking Hotline Information with them (1-844-888-FREE, help@befree.org).

- General

We understand that:

  - The Declaration will be kept on file for a period of 10 years.

  - The Declaration will be updated every year or more often as appropriate.

  - We must inform NRC immediately in the event that there is a change to the Declaration.

  - NRC may perform checks to verify that the ethical standards are adhered to and shall be granted reasonable access to our premises and to our documentation, computer systems etc, in order to be allowed to do so.

  - In the event that NRC deem that we fail to meet or are not taking appropriate steps to meet, the ethical standards, NRC may immediately terminate any and all contracts and agreements we have with them and at no cost to NRC.

- Requirement to notify NRC

We shall immediately notify NRC through the Complaints and Feedback Mechanism, provided by the NRC contract focal point if:

  - Any allegations of alleged corruption, sexual exploitation or abuse, or child abuse are made against us or, to the best our knowledge, our Representatives, during the Contract, whether relating to the Contract or not.

  - Any allegations are made, or any changes occur, in relation to any of the declarations made herein

Signed on our behalf as follows:

| Signature |  |
| --- | --- |
| Name |  |
| Position |  |
| Date |  |
| Place |  |