REQUEST FOR PROPOSAL – NRC SUDAN – TERMS OF REFERENCE (TOR) FOR National Partner Group Cash Transfer Outcome Monitoring The Request for Proposal reference: RFP-SD-PZU-061 Evaluation Terms of Reference for National Partner Group Cash Transfer Outcome Monitoring # Background information 1.1 Background on the context NRC re-entered Sudan in 2020 and established its operational footprint in multiple locations affected by conflict and displacement. NRC is an international humanitarian organization that works to support populations or people affected by displacement in contexts affected by armed conflict, violence, disasters caused by natural hazards, the adverse effects of climate change and generalized violence. NRC is currently implementing programming across NRC’s five core competencies: Wash, Camp coordination and camp management, Shelter and settlements, Information, counselling and legal assistance. Through implementation, NRC integrates cash and market-based approaches, advocacy, digital modes of assistance, and co-leads various humanitarian coordination platforms. Deadline for application is 4th June 2026 @ 16:00 (GMT +2) PROCESS FOR APPLICATION We are opened to provide further information (background of this assignment/consultancy, generic terms & conditions, information on award process) upon request. - Deadline for submission: 4th June 2026 @ 16:00 (GMT +2) Complete Proposal documents must be submitted by EMAILS Email for submission: sd.procurement@nrc.no CONTENT OF REQUEST FOR PROPOSAL - Terms of reference - How to Apply Annex 1: Applicant checklist

- TERMS OF REFERENCE

# Purpose of the evaluation and intended use

Overview of the context

As of early 2026, Sudan remains the world’s most severe humanitarian and displacement crisis, characterized by a fragmented security landscape and a near-total collapse of basic services. According to the 2026 OCHA Humanitarian Needs and Response Plan (HNRP), approximately 33.7 million people—nearly 60% of the population—require urgent humanitarian assistance, marking a 10% increase from the previous year. The conflict has resulted in the displacement of nearly 14 million people, including 9.1 million internally displaced persons (IDPs), many of whom are residing in overcrowded camps or informal settlements with minimal access to life-saving resources. The operational environment is defined by severe access constraints. Active frontlines, bureaucratic impediments, and damaged infrastructure have rendered large portions of the country, particularly in the Darfur and Kordofan regions, "hard-to-reach." In these areas, food insecurity has reached catastrophic levels (IPC Phase 5), and 70% of health facilities are non-functional. In alignment with the 2026 HNRP "Humanitarian Reset," the response has shifted toward a bottom-up, field-driven approach that prioritizes localization. This strategy acknowledges that local actors, Mutual Aid Groups (MAGs), and Emergency Response Rooms (ERRs) are often the only entities capable of maintaining a sustained presence in high-risk zones. By providing Group Cash Transfers (GCTS), NRC seeks to empower these local groups to provide agile, culturally appropriate, and timely assistance to the most vulnerable communities who are otherwise cut off from international aid pipelines.

- Scope

The scope of this assignment is to support the implementation of an Outcome Monitoring Exercise for activities implemented through NRC’s Group Cash Transfer (GCT) modality. The exercise will focus on collecting primary data from GCT focal points and end beneficiaries who are benefiting from services provided by GCT-supported groups in selected project locations. The selected national partner will be responsible for coordinating and conducting field-level data collection in accordance with NRC guidance and established monitoring tools. Data will primarily be collected through key informant interviews with GCT focal points, as well as household-level surveys or interviews with end beneficiaries to assess access to and satisfaction with services delivered by GCT groups. The assignment will include coordination with local authorities where required to obtain the necessary permissions for field activities, mobilization and supervision of enumerators, and ensuring that data collection is conducted in line with NRC’s ethical standards, safeguarding principles, and data protection policies. Particular attention will be given to ensuring safe and inclusive participation of vulnerable groups and equitable representation of beneficiaries reached through GCT interventions. Data collected through this exercise will be shared with NRC for cleaning, analysis, and reporting. The findings will contribute to measuring the outcomes of GCT-supported services, assessing the effectiveness of the GCT modality, identifying challenges and good practices, and informing program adaptation and future humanitarian responses in hard-to-reach areas.

__________________________________________

| - Project Summary |  |
| --- | --- |
| Since the escalation of conflict in Sudan in April 2023, the humanitarian landscape has dramatically shifted. Traditional aid actors face growing access restrictions, insecurity, and administrative barriers. In this vacuum, Local Responders (LRs) – including Community-Based Organizations (CBOs), youth- and women-led initiatives, and Mutual Aid Groups (MAGs) – have emerged as the primary front-line actors. Through NRC’s Group Cash Transfer (GCT) model, these LRs have been empowered with direct financial and technical support to deliver lifesaving assistance, enhance coordination, and strengthen local ownership of response mechanisms. |  |
| - Objective |  |
| The overall objective of the assignment is to support NRC in assessing the outcomes and effectiveness of interventions implemented through the Group Cash Transfer (GCT) modality. Specific objectives include: Evaluate the extent to which the assistance delivered through GCT-supported groups addressed the priority needs of targeted communities and contributed to improving access to essential services or support. Collect feedback from end beneficiaries regarding the relevance, quality, accessibility, and timeliness of the services provided through GCT groups. Generate reliable field-level data that will enable NRC to identify strengths, gaps, and lessons learned in the implementation of the GCT modality and inform future programming. Ensure that NRC and its partners remain accountable to affected populations, donors, and stakeholders by systematically monitoring outcomes and documenting the results of humanitarian assistance delivered through GCT groups. Provide insights on the effectiveness of working with local groups and community-based structures under the GCT modality in delivering humanitarian assistance in hard-to-reach and conflict-affected areas. |  |
| Roles and Responsibilities |  |
| Local Partner role | NRC role |
| - Coordinate with the relevant authorities and the HAC to obtain the necessary permissions for field data collection. | - Draft data processing agreement and Develop data collection tools. |
| - Lead and supervise data collection efforts through Household Surveys in the field. | - Provide guidance and training for the partner staff and volunteers on GCT Outcome Monitoring tool and the methodologies for data collection. |
| - Share raw data with the NRC for processing, analysis, and report drafting. | - Perform data analysis and draft the report. |
| 2.4 NRC will provide the following: |  |
| - Data collection tools. - Training on the GCT Outcome Monitoring tool and data collection methodologies. - A contact list of GCT group focal points, including their geographical coverage, will be provided. - A list of end beneficiaries may also be shared, where available; otherwise, the partner will be required to coordinate with GCT focal points to obtain it. |  |

Partner’s duties

- Obtain Approvals: Coordinate with the relevant authorities and the HAC to obtain the necessary permissions for field data collection. - coordinate with other partners to get contact lists when necessary. - Conduct Field Data Collection: Lead and supervise data collection efforts through Household Surveys - Data Dissemination: Share raw data with the NRC for processing, analysis, and report drafting, facilitating streamlined output.

- NRC’s duties

- NRC shall contribute to the completion of the Assignment in good faith - NRC shall share relevant information and documentation which is necessary for the completion of the assignment. - All requests from the Consultancy shall be replied to without undue delay. - The NRC shall, without undue delay, give notice of circumstances that the NRC understands, or ought to understand, may be of relevance to the completion of the Assignment, including any expected delays

3.4 Data protection

3.4.1 Data retention and deletion 1. The Data Receiver shall not retain or process Shared Personal Data for longer than is necessary to carry out the Agreed Purposes. 2. The Data Receiver shall ensure that any Shared Personal Data are returned to the Data Discloser or deleted (or destroyed if it is in hardcopy format) in the following circumstances: (a) on termination of the Agreement for whatever reason; (b) on expiry of the Agreement (unless extended further to the terms of this Agreement); (c) once processing of the Shared Personal Data is no longer necessary for the purposes it was originally shared for - Confidentiality and security of personal data 1. Both parties shall take all the necessary technical and organizational measures to protect the personal data transferred under this agreement against accidental, or unauthorized destruction, accidental loss, unauthorized access, use, alteration or dissemination, and against all other unauthorized forms of processing. 2. Both parties must implement the necessary technical and organizational measures to protect the confidentiality, privacy, integrity, availability, and security of the personal data including establishing organizational polices for employees to safeguard the personal data accordance with this agreement. 3. The shared personal data shall remain in the position of the receiving party authorized processors only and be processed directly by them, as determined in consultation with data discloser.

Security Risks and mitigation plans

| Risk | Consequence | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Continues conflict leading to more displacement of IDPs to the camps | Medium | Low | The project team willl work closley with local authorities and other humanitarian organisiations present to ensure effective response to influx |
| Local authorities are unsupportive or increase bureaucratic restrictions/delays | Severe impact | Medium | The project will work closely with local authorities to ensure their participation and support through project implementation |
| Lack of cooperation of key stakeholders including government authorities in support of NRC’s activities. | Severe impact | Medium | Participation in relevant coordination forums. Constant enagement with relevant government authorites theorugh out the project duration |
| Lack of cooperation of effective coordination with humanitarian partners | Medium | Medium | Ensure effective communication and coordination with partners to promote effecicitn utilisation of resources to reach beneficiries |
| Unstability in the political situation. | High | High | Following the situation and adhering to HSS department advise to find ways to continue with the operation without exposing staff or beneficiaries to any risks Regular stakeholder mapping and proactive engagement with authorities to preserve operational continuity. |
| Aid diversion or manipulation of beneficiary lists through community structures | Possible | Severe | Transparent vulnerability criteria, cross-verification through community committees, post-distribution monitoring, third-party spot checks. |
| Increasing inflation impacting procurement and budget predictability | Likely | Severe | USD-based framework agreements, electronic voucher systems, international vendor accounts, and exploration of cross-border procurement options. Conduct frequent market price and availability monitoring |
| Bureaucratic access constraints from authorities delaying or blocking field access | Likely. | Severe | Proactive engagement with authorities, transparent communication on NRC strategy and routes, and compliance with approval processes and documentation requirements.. |
| Protection risks within programming (SEA, child protection, safeguarding) | Likely. | Severe | Enforcement of NRC safeguarding policies, mandatory Code of Conduct signing, staff training, whistleblowing mechanisms, and independent CFRM reporting lines. |
| Climate-related shocks (floods, droughts) exacerbating conflict and disrupting operations | Likely. | Severe | Climate adaptation planning, alternative route mapping, integration of weather constraints into programming. Flood mitigation measures in site planning, elevated shelter foundations, drainage improvements, and seasonal contingency stocks. |

Annex 1

| State | Locality |
| --- | --- |
| Aj Jazirah | Al Hasahisa |
| Aj Jazirah | Sharg Aj Jazirah |
| Central Darfur | Azum |
| Central Darfur | Bendasi |
| Central Darfur | Mukjar |
| Central Darfur | Um Dukhun |
| Central Darfur | Wadi Salih |
| Central Darfur | Zalingi |
| East Darfur | Abu Jabrah |
| East Darfur | Abu Karinka |
| East Darfur | Ad Duayn |
| East Darfur | Ad Du'ayn |
| East Darfur | Adila |
| East Darfur | Al Firdous |
| East Darfur | Assalaya |
| East Darfur | Bahr Al Arab |
| East Darfur | Shiaria |
| East Darfur | Shia'ria |
| East Darfur | Yassin |
| Gedaref | Madeinat Al Gedaref |
| Kassala | Halfa Aj Jadeedah |
| Kassala | Madeinat Kassala |
| Kassala | Reifi Gharb Kassala |
| Kassala | Reifi Hamashkureib |
| Khartoum | Jebel Awlia |
| Khartoum | Khartoum |
| Khartoum | Sharg An Neel |
| North Darfur | Al Fasher |
| North Darfur | Al Koma |
| North Darfur | Al Lait |
| North Darfur | Al Malha |
| North Darfur | As Serief |
| North Darfur | At Tawisha |
| North Darfur | Dar As Salam |
| North Darfur | Kebkabiya |
| North Darfur | Kelemando |
| North Darfur | Kernoi |
| North Darfur | Kutum |
| North Darfur | Melit |
| North Darfur | Tawila |
| North Darfur | Um Baru |
| North Darfur | Um Kadadah |
| North Kordofan | Bara |
| North Kordofan | Sheikan |
| River Nile | Abu Hamad |
| River Nile | Ad Damar |
| River Nile | Al Buhaira |
| River Nile | Al Matama |
| River Nile | Atbara |
| River Nile | Barbar |
| River Nile | Shendi |
| Sennar | Ad Dinder |
| Sennar | Sennar |
| Sennar | Sharg Sennar |
| South Darfur | Beliel |
| South Darfur | Buram |
| South Darfur | Gereida |
| South Darfur | Kas |
| South Darfur | Kubum |
| South Darfur | Mershing |
| South Darfur | Nyala Janoub |
| South Darfur | Nyala Shimal |
| South Darfur | Rehaid Albirdi |
| South Darfur | Sharg Aj Jabal |
| South Darfur | Tulus |
| South Kordofan | Abu Kershola |
| South Kordofan | Al Buram |
| South Kordofan | Al Leri |
| South Kordofan | Dilling |
| South Kordofan | Habila - SK |
| South Kordofan | Heiban |
| South Kordofan | Kadugli |
| South Kordofan | Talawdi |
| South Kordofan | Um Durein |
| West Darfur | Ag Geneina |
| West Darfur | Beida |
| West Darfur | Foro Baranga |
| West Darfur | Habila - WD |
| West Darfur | Jebel Moon |
| West Darfur | Kereneik |
| West Darfur | Kulbus |
| West Darfur | Sirba |
| White Nile | Ad Diwaim |
| White Nile | Kosti |
| White Nile | Tendalti |

- HOW TO APPLY: PROPOSAL (EMAIL)

The applicant(s) is/are expected to comply with the below requirements and submit the following:

- Submission of proposal via email - (attach two files for each technical and financial proposal) - sd.procurement@nrc.no

.

In both cases, please make sure to write on the subject of the email the reference of this Request for Proposal as follows:

FINANICAL PROPOSAL SUBMISSION (MANADATORY)

BID PRICE FOR SERVICE CONTRACT

- The contract will be awarded to a single bidder, unless otherwise specified in the Bid Data Sheet, all duties, taxes and other levies payable by the supplier/NRC under the contract, shall be included in the total bid price submitted by the bidder.

- The priced offer submitted by Bidders shall be checked for arithmetical errors and for what might be considered unreasonable rates during the evaluation. Where errors are identified one or more of the following steps may be taken

  - By default, the financial evaluation of the bid will be based on the unit rate of the line item,

  - If any rates are considered to be unrealistic or unreasonable, they may be altered by mutual agreement, provided that no alteration shall be made in the amount of the Bid.

  - If any arithmetical errors are detected in an otherwise acceptable bid, then the Bidder will be disqualified, the onus is on the Bidder to provide accurate information.

- The Bidder is reminded that it is entirely his responsibility to ensure the accuracy of their bid. No alteration will be made to the bid after its submission on the grounds of any arithmetical errors subsequently discovered except as provided above.

- The consultant will take on any international and local tax obligations within the contract value, including a 10% Tax payable by the consultant as per Sudanese government regulations, paid by NRC.

CURRENCIES OF BID AND PAYMENT

- All prices shall be quoted by the Bidder in EURO /USD unless otherwise stated. Similarly, all payments will be made in the same currency.

- By default, payment will be made within 30 days of completion of delivery and submission of all necessary documentation (Final Report). Failure to provide all necessary documents will result in delays

BID VALIDITY

- Bids shall remain valid for a period of 90 calendar days after the date of the bid submission deadline as prescribed by Norwegian Refugee Council.

- In exceptional circumstances, prior to the expiration of the bid validity period, the Norwegian Refugee Council may request Bidders in writing to extend the period of validity of their bids. A Bidder must confirm in writing his acceptance of the extension.

- Any corrections/ amendments must be initialled and stamped by the bid

Proposed Evaluation Criteria

- Technical Evaluation “

| # | Criteria | Description | Score |
| --- | --- | --- | --- |
| 1 | Technical and Operational Capacity | 1. Monitoring and Data Collection Experience Demonstrated experience conducting household surveys, KIIs, outcome monitoring, post-distribution monitoring, assessments, or similar MEAL exercises. Experience using digital data collection tools is preferred. Proposals should clearly describe previous assignments and geographic scope. 2. Field Team and Human Resources Capacity Availability of qualified staff, supervisors, and enumerators capable of conducting field activities across target locations. Consideration should include local language capacity, gender balance, and supervisory structures. 3. Experience Working with Local Responders and Community Structures Demonstrated experience working with CBOs, Mutual Aid Groups, ERRs, community committees, or similar local structures. Experience supporting community-based approaches is preferred. | 35 |
| 2 | Contextual Understanding and Access | 4. Understanding of Sudan Humanitarian Context, and Group Cash Transfers Modality Demonstrated understanding of Sudan's conflict dynamics, displacement patterns, humanitarian access constraints, and localized response mechanisms. Experience working in conflict-affected and hard-to-reach areas is required. 5. Geographical Presence and Access Capacity Existing operational presence or networks within target states and localities. Ability to safely access locations and maintain field operations despite contextual constraints. 6. Coordination and Local Acceptance Ability to coordinate with HAC, local authorities, community leaders, and humanitarian actors to secure permissions and facilitate implementation. | 25 |
| 3 | Safeguarding, Data Protection and Delivery Approach | 7. Safeguarding and Protection Standards Demonstrated policies and practices related to PSEA, child protection, safeguarding, and ethical engagement with communities. Experience ensuring safe participation of vulnerable populations is preferred. 8. Data Protection and Confidentiality Capacity Demonstrated ability to securely collect, store, manage, and transfer personal data in accordance with NRC requirements and ethical standards. 9. Delivery Methodology and Risk Management Clear and feasible approach for field implementation including supervision arrangements, risk mitigation measures, quality assurance, and contingency planning for insecure environments. | 25 |
| 4 | Financial Offer (Cost Effectiveness) | 10. Financial Proposal – Realism and Value for Money Realism, clarity, and transparency of the financial proposal including staffing, transportation, field deployment, operational costs, and implementation assumptions. Proposals will be assessed on value for money rather than lowest cost alone. | 15 |
|  | TOTAL |  | 100 |

ANNEX I - APPLICATION CHECKLIST (FOR THE APPLICANT TO FILL AND SIGN/ STAMP)

TO BE INCLUDED IN THEIR PROPOSAL

| Description – ANNEX I | To be filled by bidder Included? (yes/no) | To be filled by NRC |  |  |
| --- | --- | --- | --- | --- |
|  |  | Present & complete? |  | Comments |
| ENVELOP – TECHNICAL |  |  |  |  |
| CV of the applicants |  |  |  |  |
| Cover letter detailing the consultant’s qualifications and experience in undertaking similar assignments; |  |  |  |  |
| Copies of Consultant ID and address for screening purposes |  |  |  |  |
| Proof of consultancy registration/ Company profile |  |  |  |  |
| Tax Identification Number (TIN) registration certificate (Tax registration)- If any |  |  |  |  |
| Value Added Tax (VAT) registration certificate (if VAT is to be charged in the country of origin of the consultant) – if any |  |  |  |  |
| All necessary license certificates in line with government regulations |  |  |  |  |
| Envelop 2 – Financial |  |  |  |  |
| Section 6 – Pricing proposal - signed/ stamped |  |  |  |  |

| # | Question | Response Requirement |
| --- | --- | --- |
| 1 | Please describe your understanding of the assignment, including key contextual considerations for conducting outcome monitoring of Group Cash Transfer (GCT) interventions in Sudan. |  |
| 2 | Describe your proposed methodology for conducting field data collection, including household surveys, KIIs with GCT focal points, supervision of enumerators, and coordination with local authorities. |  |
| 3 | Explain how your approach will ensure data quality, ethical standards, safeguarding, inclusion of vulnerable groups, and adherence to Do No Harm principles. |  |
| 4 | Describe your experience conducting MEAL activities such as household surveys, PDMs, outcome monitoring, assessments, or similar data collection exercises in humanitarian or conflict settings. |  |
| 5 | Describe your experience working in Sudan or other hard-to-reach/conflict-affected contexts, including coordination with local authorities and community structures. |  |
| 6 | Provide a detailed workplan and timeline for the assignment, including field deployment plan, supervision structure, and data submission schedule. |  |
| 7 | Identify key operational risks (access, security, data collection challenges, community engagement) and mitigation measures. |  |
| 8 | Provide a detailed financial proposal in USD, including enumerator costs, transport, supervision, data collection tools, and all operational expenses. |  |
| 9 | Submit CVs of key personnel including field supervisors, enumerators lead, and data manager (if applicable). |  |
| 10 | Provide examples of previous similar MEAL assignments (household surveys, outcome monitoring, PDM, humanitarian assessments). |  |
| 11 | Provide at least three professional references from similar assignments. |  |
| 12 | Submit company registration and legal documentation (if applicable). |  |

To: Norwegian Refugee Council

Sir / Madam,

We offer to deliver the service in accordance with all requirements of the current Request for Proposal, Conditions of Contract and any other Binding requirements accompanying this Bid. We, the undersigned, verify that we are in compliance with all applicable laws and regulations, and meet the ethical standards as listed above or positively agree to these ethical standards and are willing to implement necessary changes in the organization.

This Bid signed by our authentic representative and your written award of it shall constitute the formation of a binding contract between us.

| Registered company name: |  |
| --- | --- |
| Any other trading names: |  |
| Any associated companies (cross holding/ joint ownership/ shareholding/ etc.) |  |
| Name of Signatory: | Date of Signing: |
| Title of Signatory: | Name of Bidder: |
| Signature & stamp: | Tel N°: |
|  | Email: |
|  | Address: |

| Bank name (to be used for this contract) |  |
| --- | --- |
| Account number |  |

Ethical Standards Declaration for all Supply, Service and Works Contractors

We, the undersigned, (‘we’, ‘our’ or ‘us’) CONSIDERING THAT:

FIRST, we are bidding for, or entering into, a contract with the Norwegian Refugee Council (NRC) to supply goods, services or works to NRC (‘the Contract’).

SECOND, we understand that as a humanitarian organisation, NRC expects its suppliers and contractors to have high ethical standards.

THIRD, we understand that NRC therefore needs us to confirm that we adhere to the required ethical standards (‘the ethical standards’) by signing this declaration (‘the Declaration’).

THEREFORE, we DO HEREBY DECLARE as follows:

- Declaration concerning compliance with applicable laws and these ethical standards

We declare that we shall:

- Meet the ethical standards in this declaration (‘ethical standards’)

- Ensure that any party representing us, including but not limited to:

•	board members

•	directors

•	employees

•	contractors or sub-contractors, and their employees

•	consultants and sub-consultants, and their employees;

•	other legal representatives

(‘our Representatives’) are aware of and comply with these ethical standards.

In the event that we, or our Representatives, do not meet the ethical standards at present, we shall:

- Explain to NRC in what way we do not currently meet the ethical standards

- Agree a plan and timeline with NRC to implement changes that allow us to meet the ethical standards

- Provide regular updates to NRC on the implementation plan.

- Declaration concerning status

We hereby declare that neither we, nor to the best if our knowledge our Representatives, are in any of the following situations:

  - Have made an offer, payment, consideration or benefit of any kind, which constitutes illegal or corrupt practice, directly or indirectly, as an inducement or reward in relation to the tendering, awarding or execution of the Contract.

  - Are involved in any form of fraud, corruption, collusion, coercive practice, bribery, involvement in a criminal organisation or other illegal activity

  - Are insolvent, in receivership, bankrupt, or being wound up

  - Have suspended activities

  - Are subject to legal proceedings related to 2.1

  - Have at any time been found guilty and sentenced by a court, whether in the country of employment or abroad, for a criminal offence in respect of children or vulnerable adults

  - Are engaged in:

•	terrorism or the material support of terrorism

•	the sale or manufacture, either directly or indirectly, of anti-personnel mines or any components produced primarily for the operation thereof

•	the sale or manufacture, either directly or indirectly, of weapons

•	the production of alcohol, tobacco, or pornography.

- Declaration concerning Conflicts of Interest

We declare that neither we nor, to the best of our knowledge, our Representatives have an undisclosed conflict of interest with NRC, in accordance with NRC’s Conflict of Interest Policy (the Policy).

Where any potential conflict of interest exists between our Representatives and NRC or any NRC staff member, we shall notify NRC in writing of the potential conflict using Form F in the Policy. We understand that the Policy and the Form is available on NRC’s website or that we can contact the NRC Procurement focal point, as mentioned in the tender documentation. NRC shall then determine whether action is required.

A conflict of interest can be due to a relationship with an NRC staff member such as family or friends.

We understand that if we fail to report a potential conflict of interest and are later found to have a conflict of interest, we may be removed from the NRC vendor database.

- Declaration concerning compliance with national law

We declare that we and, to the best of our knowledge, our Representatives:

  - comply with all applicable laws and regulations in effect in the country or countries where the Contract will be carried out.

  - comply with all applicable export laws concerning the country or countries where the Contract will be carried out.

  - are registered with the relevant government authority with regard to taxation for the duration of the Contract.

  - pay taxes according to all applicable national laws and regulations for the duration of the Contract.

- Declaration concerning compliance with labour standards

We declare that we and, to the best of our knowledge, our Representatives:

We declare that we and, to the best of our knowledge, our Representatives comply with applicable national labour law standards and the International Labour Organisation Declaration on Fundamental Principles and Rights at Work.

Specifically, we declare that we and, to the best of our knowledge, our Representatives comply with the following minimum labour standards:

  - Working Conditions

- All workers receive a contract of employment that is written in a language they understand.

- All workers are free to leave after giving reasonable notice.

- All workers have the right to join or form trade unions of their own choosing and to bargain collectively.

- No worker is required to lodge ‘deposits’ or identity papers or immigration documents in order to obtain employment.

  - Wages and benefits

  - Wages and benefits paid for a standard working week meet, at a minimum, national legal standards or industry benchmark standards, whichever is higher. Wages are always sufficient to meet basic needs.

  - No deductions from wages are made as a disciplinary measure.

  - Working time

  - Working hours comply with national laws and benchmark industry standards, whichever affords greater protection. Whenever possible working hours do not exceed 48 hours per week (8 hours per day).

  - Workers are provided with at least one day off for every 7-day period.

  - Health and safety

  - Steps are taken to prevent accidents and injury to health arising out of, associated with, or occurring in, the course of work, by minimizing, so far as is reasonably practicable, the causes of hazards inherent in the working environment.

  - Workers receive regular and documented health and safety training, and such training is repeated for new workers.

  - Workers have access to clean toilet facilities and to potable water, and, if appropriate, sanitary facilities for food storage is provided.

  - Accommodation, where provided, is clean, safe and adequately ventilated.

  - Discrimination and abuse

  - No worker is forced, bonded or an involuntary prison worker.

  - There is no discrimination at the workplace based on ethnic background, religion, age, disability, gender, marital status, sexual orientation, union membership or political affiliation.

  - Measures are in place to protect workers from sexually intrusive, threatening, insulting or exploitative behaviour, and from discrimination or termination of employment on unjustifiable grounds, e.g. marriage, pregnancy, parenthood or HIV status.

  - Physical abuse or punishment, or threats of physical abuse, sexual or other harassment and verbal abuse, as well as other forms of intimidation, are prohibited.

  - Persons under 18

- No persons under the age of 18 shall be engaged in work which is hazardous to their health or safety, including night work.

- The working hours and nature of work of any worker who is under the age of 18 shall not interfere with their opportunity to complete his or her education.

- Declaration concerning the environmental standards

We declare that we and, to the best of our knowledge, our Representatives comply with applicable national environmental law standards and with international environmental standards, to the greatest extent possible.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We respect national and international environmental legislation and regulation.

  - We ensure that production and extraction of raw materials for production does not contribute to the destruction of the resources and income base for marginalised populations, such as in claiming large land areas or other natural resources on which these populations are dependent.

  - We take environmental measures into consideration throughout the production and distribution chain ranging from the production of raw material to the consumer sale. This includes reasonable steps to minimise negative environmental impacts (e.g. emissions, water usage, waste) and to use - where possible - sustainable resources. Local, regional and global environmental aspects shall be considered. The local environment at the production site will not be exploited or degraded by pollution and waste.

  - We carefully manage hazardous chemicals and other substances in accordance with documented safety procedures.

- Declaration concerning protection from sexual exploitation and abuse

We and, to the best of our knowledge, our Representatives comply with international standards related to protection from sexual exploitation and abuse (PSEA) and sexual harassment.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We take sexual misconduct seriously and ensure that any employee found to have carried out sexual misconduct will be subject to disciplinary action.

  - We will ensure, that none of our employees engage in any sexual activity with persons (adult or child) in relation with this contract regardless of the age of majority or consent locally.

  - We will ensure that none of our employees produce, procure, distribute or use sexually explicit material in any activities under the Contract or on any sites used under the Contract.

  - We will ensure that none of our employees will exchange money, employment, goods or services for sex, including sexual favours or other forms of humiliating, degrading, or exploitative behaviour.  This prohibition extends to any use of sex trade workers.  If  any sexual misconduct is found to have taken place, such employees face disciplinary action.

  - We shall report any incident or complaint of sexual misconduct or child abuse related to the activities carried out under the Contract through NRC’s PSEA and Safeguarding Unit at psea@nrc.no.

  - We shall report any known or reported sexual relationship between our employees and NRC staff to NRC.

- Declaration concerning protection of children

We declare that neither we nor, to the best of our knowledge, our Representatives are engaged in any practice inconsistent with the rights set forth in the Convention on the Rights of the Child.  We commit to upholding international and national laws and policies regarding child safeguarding.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We support and protect the complainant, survivors and witnesses of any raised incidents or complaints of sexual misconduct or child abuse.

  - We will ensure, that our employees will not abuse or exploit children or act in a manner that may place a child at risk of harm.

  - We will ensure that our employees are not left alone with children.

  - We will ensure our employees will not ask children for personal contact details without a valid reason to do so.

  - We listen, to the best of our ability, to children’s views and opinions and treat boys and girls in a manner that is respectful of their rights and dignity during the performance of the Contract.

  - We shall report any suspicion of child safeguarding concerns through the Complaints and Feedback Mechanism, provided by the NRC contract focal point and at https://nrc.caseiq.app/portal for reporting safeguarding concerns i.e. the speak up portal for 3rd parties.

- Declaration concerning anti-human trafficking

We declare that neither we nor, to the best of our knowledge, our Representatives are engaged in trafficking in persons as defined in the protocol to Prevent, Suppress and Punish Trafficking in Persons or the UN Convention against Transnational Organized Crime.

Specifically, we declare that we and, to the best of our knowledge, our Representatives adhere to the following standards:

  - We do not solicit persons for the purpose of employment, or offer employment by means of materially false or fraudulent pretences, representations, or promises.

  - We do not charge employees recruitment fees.

  - We do not provide or arrange housing for employees that does not meet host country housing and safety standards.

  - We commit to report any suspected violations of this clause to NRC immediately.

  - We commit to make our Representatives aware of the trafficking related prohibitions outlined above and share the Global Human Trafficking Hotline Information with them (1-844-888-FREE, help@befree.org).

- General

We understand that:

  - The Declaration will be kept on file for a period of 10 years.

  - The Declaration will be updated every year or more often as appropriate.

  - We must inform NRC immediately in the event that there is a change to the Declaration.

  - NRC may perform checks to verify that the ethical standards are adhered to and shall be granted reasonable access to our premises and to our documentation, computer systems etc, in order to be allowed to do so.

  - In the event that NRC deem that we fail to meet or are not taking appropriate steps to meet, the ethical standards, NRC may immediately terminate any and all contracts and agreements we have with them and at no cost to NRC.

- Requirement to notify NRC

We shall immediately notify NRC through the Complaints and Feedback Mechanism, provided by the NRC contract focal point if:

  - Any allegations of alleged corruption, sexual exploitation or abuse, or child abuse are made against us or, to the best our knowledge, our Representatives, during the Contract, whether relating to the Contract or not.

  - Any allegations are made, or any changes occur, in relation to any of the declarations made herein

Signed on our behalf as follows:

| Signature |  |
| --- | --- |
| Name |  |
| Position |  |
| Date |  |
| Place |  |